## Donwood Master Gantt
Project Name : Donwood – Payment & Website Upgrade
Project Start: 12-Dec-25
End Date: 22-Dec-25
Total Days and Hours: 10 Days (50 Hours) | [7 empty] | Friday | Monday | Friday
Task ID | Task | Project Lead | Start Date | End Date | Total Hours | Balance Hours | Progress | 2025-12-12 | 2025-12-15 | 2026-01-01
1 | Payment Gateway Issues - Upgrading files to PHP version | Sanil | 2025-12-12 | 2025-12-19 | 35
1.1 | Changing the Code Payment Files from PHP Version 5.6 to 8.* to Use Modern Tokenization and Hosted Fields |  |  |  | 25 | 11 | 56% | 3 | 3 | 8 | 14
1.2 | Sandbox Testing - To Check if the Payment is Going Through |  |  |  | 2 | 0 | 100% |  |  | 2 | 2
1.3 | Upgrading the Helper Classes FxmCommWebParser.php and FxmCommWebMerchant.php to PHP 8.* |  |  |  | 5 | 1 | 80% |  |  | 4 | 4
1.4 | Add Proper Error Logging |  |  |  | 3 | 3 | 0% |  |  |  | 0
2 | Website Changes | Sanil | 2025-12-17 | 2025-12-22 | 15 |  | 0% |  |  |  | 0
2.1 | Add Phone Number (95425370) | [9 empty] | 0
2.2 | Issues Regarding Pre-Paid and previous year order | [9 empty] | 0
2.3 | Mobile Friendly Issue | [9 empty] | 0
2.4 | Cannot click on cart to view order | [9 empty] | 0
2.5 | Website doesn’t open on page to enter school code | [9 empty] | 0
2.6 | Ability to upload year 12 only - Need to Discuss with Client | [9 empty] | 0
2.7 | Ability to have a mail out system built into website. | [9 empty] | 0