## Donwood Master Gantt
Project Name : Donwood – Payment & Website Upgrade
Project Start: 12-Dec-25
End Date: 22-Dec-25
Total Days and Hours: 10 Days (50 Hours) | [7 empty] | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday
Task ID | Task | Project Lead | Start Date | End Date | Total Hours | Balance Hours | Progress | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22
1 | Payment Gateway Issues - Upgrading files to PHP version | Sanil | 2025-12-12 | 2025-12-19 | 35
1.1 | Changing the Code Payment Files from PHP Version 5.6 to 8.* to Use Modern Tokenization and Hosted Fields |  |  |  | 25 | 19 | 24% | 3 | 3 | [5 empty] | 6
1.2 | Sandbox Testing - To Check if the Payment is Going Through |  |  |  | 2 | 2 | 0% | [7 empty] | 0
1.3 | Upgrading the Helper Classes FxmCommWebParser.php and FxmCommWebMerchant.php to PHP 8.* |  |  |  | 5 | 5 | 0% | [7 empty] | 0
1.4 | Add Proper Error Logging |  |  |  | 3 | 3 | 0% | [7 empty] | 0
2 | Website Changes | Sanil | 2025-12-17 | 2025-12-22 | 15 |  | 0% | [7 empty] | 0
2.1 | Add Phone Number (95425370) | [13 empty] | 0
2.2 | Issues Regarding Pre-Paid and previous year order | [13 empty] | 0
2.3 | Mobile Friendly Issue | [13 empty] | 0
2.4 | Cannot click on cart to view order | [13 empty] | 0
2.5 | Website doesn’t open on page to enter school code | [13 empty] | 0
2.6 | Ability to upload year 12 only - Need to Discuss with Client | [13 empty] | 0
2.7 | Ability to have a mail out system built into website. | [13 empty] | 0